## Forms
Module | Form / Report Name | Description | Completed | Progress (%) | Date Completed | 0
User Functions | Swipes History | Shows the employee's swipes history by period | Completed | 100
| Absences History | Shows the employee absences | Completed | 100
| Leave History | Shows the employee's leave history | Completed | 100
| Leave Balance Inquiry | Shows the employee's leave balance information | Completed | 100
| Attendance History | Shows the Timesheet records by pay period | Completed | 100
| DIL Entitlements Inquiry | Shows the employee's DIL entitlement balance and any inactive DILs. | Completed | 100
| View Current Shift Pattern | View the employee's shift pattern information | Completed | 100
| Dependents Information | Shows the list of the employee's family dependents | Completed | 100
| Personal Legal Documents | View the legal documents information that include the CPR, resident permit, etc. | Not yet started | 0
| Employee Attendance Dashboard | Used to view the attendance status of an employee based on the swipes at the main gate entrances. | Completed | 100 | 2016-10-24
HR Functions | Timesheet Exceptional (By Pay Period) | This form is used to view the Timesheet records of an employee by pay period | Not yet started | 100
| Timesheet Correction | This form is used to modify the Timesheet record of an employee to remove no-pay-hours, absences, and lates. | Not yet started | 50
| Reason of Absence Entry | This form is used to specify the reason of absence for an employee who goes on training, business trip, sick leave and other reasons. The Timesheet process will not mark the employee absent when an entry is found here. | Completed | 100 | 2016-07-18
| Manual Timesheet Entry | Used to add Timesheet record to enter employee attendance who forgot to bring their ID badges | Completed | 100 | 2016-07-17
| Overtime & Meal Voucher Approval | Used to approve or reject the overtime of Shift Worker as well as to grant meal voucher. | Not yet started | 0
| Shift Pattern Changes (For Employee, Fire Team Member, and Contractors) - Inquiry Form - Data Entry Form | This form is used to change the shift pattern of an employee, contractor or fire team member | Completed | 100
| Assign Temp. Working Cost Center and Special Job Catalog - Inquiry Form - Data Entry Form | This form is used to assign temporay working cost center and special job catalog to specific employee | Completed | 100
| Employee Exceptional Inquiry | Used to view the number of absences, sick leaves, injury leaves, DILs, no-pay-hours, and overtimes of an employee on specified period. | Completed | 100
| Long Absence Inquiry | Used to view the list of employees who are absent or on sick leave for more than 5 days for the duration of 1 month. | Completed | 100
| On Annual Leave But Swiped Inquiry | Used to view the list of employees who went on leave but have swiped at the Main Gate / Foil Mill entrance. | Completed | 100
| Resigned But Swiped Inquiry | Used to view the list of employees who already resigned or left GARMCO but have swiped at the Main Gate / Foil Mill entrances. | Completed | 100
| Timesheet Integrity by Correction Code | Used to search for Timesheet records that match the specified correction code and date period. | Completed | 100
| Employee Directory | Used to search for the employee's contact information that include extension no., mobile no., direct no. and fax no. | Not yet started | 0
| GARMCO Calendar | Used to view the public holidays and other special days declared in GARMCO | Completed | 100
| Cost Center Managers | Used to view the list of Superintendent and Cost Center Manager in each department | Completed | 100
| Supervisors List | Used to view the list of all Shift Supervisors and Department Heads | Not yet started | 0
| Cost Center Security Setup | Used by Administrators to grant or revoke cost center permission to specific user | Not yet started | 0
| Form Security Setup | Used by Administrators to grant or revoke form-level access to specific user | Not yet started | 0
| Master Shift Pattern Setup | Used by Administrators to define new shift pattern and populate the shift codes and pointers | Not yet started | 0
| Absence Reason Report | View the absences report of all employees based on specific period and reason of absences. | Not yet started | 0
| Weekly Overtime Report | View the overtime summary of shift workers on weekly basis. | Not yet started | 0
| Aspire Employees Payroll Report | View the overtime records of Aspire employees by pay period. | Not yet started | 0
| Daily Attendance Report | This report shows the attendance records of all shift workers and salary staff employees based on specific period and cost center. | Not yet started | 0
| Day-in-lieu Report | Shows the DIL entitlements (used and not used) of all employees that belong to specific cost center. | Not yet started | 0
Secretary / Clerk Functions | Duty ROTA Entry | This form is used to view, add, edit and delete duty ROTA entries for ICT, Purchasing and Engineering departments | Not yet started | 0
| Shift Projection | This form is used to view the projected shift pattern assignment to all employees that belong to the specific cost center for the span of 1 month starting on the specified date. | Not yet started | 0
| Employee Attendance History Report | This report shows the attendance history of an employee by date period. | Not yet started | 0
| Duty ROTA Report | This report shows the attendance of ICT, Purchasing or Engineering personnel who are on duty ROTA. The total amount to be paid to the employee is summarized in this report. | Not yet started | 0
| DIL Due to Late Entry of Duty ROTA Report | This report shows the list of employees who were granted DIL entitlement by the system due to late entry of duty ROTA. | Not yet started | 0
| Punctuality Performance Report | This report is used to view the attendance performance of a particular cost center based on the number of lates and absences of emloyees within the department. | Not yet started | 0
| Contractor Attendance Report | Used to search the attendance history of a particular Contractor | Not yet started | 70
Security Personnel Functions | Visitor's Pass Inquiry | Used to search for the visitors log record | Completed | 100
| Visitor's Pass Entry | Data entry form for recording the entry of visitors and guests in the company | Completed | 100
| Visitors/ Guest Visit History Report | This report shows the visit history of a visitor or guest within the company based on specific period | Not yet started | 100
| Manual Attendance Entry | Used by Security Personnel to enter the In and Out time of employees who forgot to bring their ID badges | Not yet started | 100
| Emergency Response Team Inquiry | This form shows the current on-duty Fire Team members with their respective employee information and contact numbers. | Not yet started | 100
MIS Functions | Master Table Setup | Used by System Administrators to add, edit, and delete records in various primary and child tables which are used across the system. | Not yet started | 0
| Timesheet Validations Setup | Used by System Administrators to configure the ystem flags that are used in the Timesheet Process and Shift Pattern Update Service. | Not yet started | 0
| Site Visitor's Log | View the list of current users accessing the system that include information such as date and time of visit, username, workstation id, and the name of form or report which the user had opened. | Not yet started | 0
| Shift Pattern Update Service Log | Used by System Administrators to analyze the log history records created by the Shift Pattern Service. | Not yet started | 0
| Timesheet Processing Service Log | Used by System Administartors to analyze the log history records created by the Timesheet Processing Service. | Not yet started | 0

## Setup
Status | Modules
Completed | User Functions
Work-in-progress | Secretary / Clerk Functions
Not yet started | Security Personnel Functions
HR Functions
MIS Functions