## Project Plan
TAS Upgrade Project Plan
Module / Functionality | Form Name | Type of Functionality | Estimated Work Duration | Work Completed (%) | Status | Remarks | Date Started | Date Completed
New ID Badge System | Contractor Attendance - Inquiry Form - Attendance History Report | New | 5 days | 100 | Completed | Implemented new ID badges for contractors wherein attendance record is fetched directly from the Access System.
User Functions | Employee Self Service (Homepage) - Swipes History - Absences History - Leave History - Leave Balance - Attendance History - DIL Entitlements - Shift Pattern Information - Dependents Information | New | 4 days | 100 | Completed | Integrated the "Employee's Self Services System" which is a separate system used to view the employee's attendance records
| Employee Attendance Dashboard | Old / Existing | 3 days | 100 | Completed
| View Current Shift Pattern | Old / Existing | 2 day | 100 | Completed
Secretary / Clerk Functions | Duty ROTA Entry - Inquiry Form - Data Entry Form | Old / Existing | 4 days | 100 | Completed |  | 2016-11-02 | 2016-11-07
| Shift Projection | Old / Existing | 2 days | 100 | Completed |  | 2016-11-07 | 2016-11-08
| Employee Attendance History Report | Old / Existing | 2 days | 100 | Completed |  | 2016-11-09 | 2016-11-10
| Duty ROTA Report | Old / Existing | 2 days |  | Work in progress |  | 2016-11-10
HR Functions | Timesheet Exceptional (By Pay Period) | Old / Existing | 3 days | 100 | Completed
| Timesheet Correction - Inquiry Form - Data Entry Form | Old / Existing | 5 days | 50 | Suspended
| Reason of Absence Entry - Inquiry Form - Data Entry Form | Old / Existing | 4 days | 100 | Completed
| Manual Timesheet Entry - Inquiry Form - Data Entry Form | Old / Existing | 4 days | 100 | Completed
| Overtime & Meal Voucher Approval - Inquiry Form - Data Entry Form | Old / Existing | 4 days | 100 | Completed |  | 2016-10-27 | 2016-11-01
| Shift Pattern Changes (Employee, Fire Team Member, and Contractors) - Inquiry Form - Data Entry Form | Old / Existing | 5 days | 100 | Completed
| Assign Temp. Working Cost Center and Special Job Catalog - Inquiry Form - Data Entry Form | Old / Existing | 4 days | 100 | Completed
| Employee Exceptional Inquiry | Old / Existing | 3 days | 100 | Completed
| Long Absence Inquiry | Old / Existing | 3 days | 100 | Completed
| On Annual Leave But Swiped Inquiry | Old / Existing | 3 days | 100 | Completed
| Resigned But Swiped Inquiry | Old / Existing | 3 days | 100 | Completed
| Timesheet Integrity by Correction Code | Old / Existing | 3 days | 100 | Completed
| Employee Directory | New | 2 days | 100 | Completed | Integrated the "Employee Directory System" which is used to search for the employee's contact information that include extension no., mobile no., direct no. and fax no.
| GARMCO Calendar | New | 2 days | 100 | Completed | This form will be used to view the public holidays and other special days declared in GARMCO
| Cost Center Managers Inquiry | New | 3 days | 100 | Completed | This form will be used to view the list of all Superintendent and Cost Center Manager in GARMCO
| Absence Reason Report | Old / Existing | 2 days |  | Pending
| Weekly Overtime Report | Old / Existing | 2 days |  | Pending
| Aspire Employees Payroll Report | Old / Existing | 2 days |  | Pending
| Daily Attendance Report | Old / Existing | 2 days |  | Pending
| Day-in-lieu Report | Old / Existing | 2 days |  | Pending
| DIL Due to Late Entry of Duty ROTA Report | Old / Existing | 2 days |  | Pending
| Punctuality Performance Report | Old / Existing | 2 days |  | Pending
Security Personnel Functions | Visitor's Pass System - Inquiry Form - Data Entry Form - Visitor/Guest Visit History Report | New | 8 days | 100 | Completed | This module will be used by the Security Personnel to log the entry of all Visitors and Guests that come inside the company. The swipe data will be recorded and the history of visit will be shown in the report.
| Manual Attendance - Inquiry Form - Data Entry Form | Old / Existing | 4 days | 100 | Completed
| Emergency Response Team Inquiry | Old / Existing | 2 days | 100 | Completed
MIS Functions | Cost Center Security Setup - Inquiry Form - Data Entry Form | New | 4 days |  | Pending | This form will be used by System Administrators to grant or revoke cost center permission to specific users. Data is stored in a centralized database used by the Common Admin System.
| Form Security Setup - Inquiry Form - Data Entry Form | New | 4 days |  | Pending | This form will be used by System Administrator to grant or revoke form-level access permission to specific users. Data is stored in a centralized database used by the Common Admin System.
| Master Shift Pattern Setup - Inquiry Form - Data Entry Form | New | 4 days |  | Pending | This form will be used by System Administrator to define new shift pattern and populate the shift codes and pointers.
| Master Table Setup | New | 3 days |  | Pending | This form will be used by System Administrator to add, edit, and delete records in various primary and child tables used across the system.
| Timesheet Validations Setup | New | 3 days |  | Pending | This form will be used by System Administrator to configure various system flags which are used in the Timesheet Processing and Shift Pattern Update services.
| Website Visitor's Log | New | 3 days |  | Pending | This form will be used by System Administrator to view the list of users currently accessing the system. Information such as date and time of visit, username, workstation id, and the name of form or report which the user had opened will be displayed on the screen.
| Shift Pattern Update Service Log | New | 3 days |  | Pending | This form will be used by System Administrator to analyze the log history records created by the Shift Pattern Service.
| Timesheet Processing Service Log | New | 3 days |  | Pending | This form will be used by System Administartor to analyze the log history records created by the Timesheet Processing Service.

## Setup
Status | Type of Functionality
Work in progress | Old / Existing
Completed | New
Pending
Suspended