## Database Changes
Summary of Database Changes
DB Object Name | Database Name | DB Type | Description | File Location | Type of Change | Revision No. | Revision Date | Summary of Changes Applied | Notes | Overall Status | Date Completed
tas.OvertimeWFRoutineHistory | tas2 | Table | This table stores workflow transaction history of the "Overtime Online Approval System" | C:\NET Projects\GARMCO TAS V3\GARMCO.AMS.TAS\DBScripts\CreateScripts\Tables | Create | 1 | 2017-07-26 | New table | DB object already synchronized with the live database server | Completed | 2017-08-30
tas.OvertimeDistributionMember | tas2 | Table | This table stores the action members of a particular distribution group | C:\NET Projects\GARMCO TAS V3\GARMCO.AMS.TAS\DBScripts\CreateScripts\Tables | Create | 1 | 2017-08-15 | New table | DB object already synchronized with the live database server | Completed | 2017-08-30
tas.OvertimeRequest | tas2 | Table | This table stores information about the overtime requisition | C:\NET Projects\GARMCO TAS V3\GARMCO.AMS.TAS\DBScripts\CreateScripts\Tables | Create | 1 | 2017-07-24 | New table | DB object already synchronized with the live database server | Completed | 2017-08-30
tas.OvertimeWFEmailDelivery | tas2 | Table | This table stores email communication records for the "Overtime Online Approval System" | C:\NET Projects\GARMCO TAS V3\GARMCO.AMS.TAS\DBScripts\CreateScripts\Tables | Create | 1 | 2017-07-26 | New table | DB object already synchronized with the live database server | Completed | 2017-08-30
tas.OvertimeWFCostCenterMapping | tas2 | Table | This table stores the mapping information between specific cost center and the workflow template to use | C:\NET Projects\GARMCO TAS V3\GARMCO.AMS.TAS\DBScripts\CreateScripts\Tables | Create | 1 | 2017-07-31 | New table | DB object already synchronized with the live database server | Completed | 2017-08-30
tas.OvertimeWFApprovalHistory | tas2 | Table | This table stores approval history for the "Overtime Online Approval System" | C:\NET Projects\GARMCO TAS V3\GARMCO.AMS.TAS\DBScripts\CreateScripts\Tables | Create | 1 | 2017-07-26 | New table | DB object already synchronized with the live database server | Completed | 2017-08-30
tas.OvertimeWFActivityTemplate | tas2 | Table | This table stores the workflow activity template for the "Overtime Online Approval System" | C:\NET Projects\GARMCO TAS V3\GARMCO.AMS.TAS\DBScripts\CreateScripts\Tables | Create | 1 | 2017-07-26 | New table | DB object already synchronized with the live database server | Completed | 2017-08-30
tas.OvertimeWFTransactionActivity | tas2 | Table | This table stores the workflow transaction activities for the "Overtime Online Approval System" | C:\NET Projects\GARMCO TAS V3\GARMCO.AMS.TAS\DBScripts\CreateScripts\Tables | Create | 1 | 2017-07-26 | New table | DB object already synchronized with the live database server | Completed | 2017-08-30
fnOTDistributionGroupMembers | tas2 | UDF | Get the distribution group members | C:\NET Projects\GARMCO TAS V3\GARMCO.AMS.TAS\DBScripts\CreateScripts\UserDefinedFunctions | Create | 1 | 2017-08-02 | New UDF | DB object already synchronized with the live database server | Completed | 2017-08-30
tas.fnGetWFActionMemberOvertimeRequest | tas2 | UDF | Retrieves the workflow action member | C:\NET Projects\GARMCO TAS V3\GARMCO.AMS.TAS\DBScripts\CreateScripts\UserDefinedFunctions | Create | 1 | 2017-08-23 | New UDF | DB object already synchronized with the live database server | Completed | 2017-08-30
tas.fnGetActionMember_WithSubstitute_V2 | tas2 | UDF | Retrieves the workflow action member | C:\NET Projects\GARMCO TAS V3\GARMCO.AMS.TAS\DBScripts\CreateScripts\UserDefinedFunctions | Update | 1.1 | 2017-08-27 | Added "HEADNSUPER" distribution code | DB object already synchronized with the live database server | Completed | 2017-08-30
tas.fnCheckIfBypassOTApproval | tas2 | UDF | This function is used to check if an an approver already approved an OT requisition hence will be bypassed by the workflow engine | C:\NET Projects\GARMCO TAS V3\GARMCO.AMS.TAS\DBScripts\CreateScripts\UserDefinedFunctions | Create | 1 | 2017-08-27 | New UDF | DB object already synchronized with the live database server | Completed | 2017-08-30
tas.fnIsOTDueToShiftSpan | tas2 | UDF | This function is used to check if the overtime is a result of shift span due to double continous shift | C:\NET Projects\GARMCO TAS V3\GARMCO.AMS.TAS\DBScripts\CreateScripts\UserDefinedFunctions | Create | 1 | 2017-08-30 | New UDF | DB object already synchronized with the live database server | Completed | 2017-08-30
tas.Pr_GetOTApprovalHistory | tas2 | Stored Procedure | Get the overtime approval history records | C:\NET Projects\GARMCO TAS V3\GARMCO.AMS.TAS\DBScripts\CreateScripts\StoredProcedures | Create | 1 | 2017-08-14 | New stored procedure | DB object already synchronized with the live database server | Completed | 2017-08-30
tas.Pr_GetRequisitionApprover | tas2 | Stored Procedure | Get the approvers who had approved the overtime request | C:\NET Projects\GARMCO TAS V3\GARMCO.AMS.TAS\DBScripts\CreateScripts\StoredProcedures | Create | 1 | 2017-08-15 | New stored procedure | DB object already synchronized with the live database server | Completed | 2017-08-30
tas.Pr_UpdateOvertimeRequestByHR | tas2 | Stored Procedure | This stored procedure is used to update overtime requisition as a result of validation by HR | C:\NET Projects\GARMCO TAS V3\GARMCO.AMS.TAS\DBScripts\CreateScripts\StoredProcedures | Create | 1 | 2017-08-19 | New stored procedure | DB object already synchronized with the live database server | Completed | 2017-08-30
tas.Pr_InsertUpdateDeleteOvertime_Clerk | tas2 | Stored Procedure | This stored procedure is used in "Employee Overtime Entry" form | C:\NET Projects\GARMCO TAS V3\GARMCO.AMS.TAS\DBScripts\CreateScripts\StoredProcedures | Create | 1 | 2017-07-26 | New stored procedure | DB object already synchronized with the live database server | Completed | 2017-08-30
tas.Pr_GetOvertimeWFEmailDelivery | tas2 | Stored Procedure | This stored procedure is used to get the workflow emails pending for delivery | C:\NET Projects\GARMCO TAS V3\GARMCO.AMS.TAS\DBScripts\CreateScripts\StoredProcedures | Create | 1 | 2017-08-01 | New stored procedure | DB object already synchronized with the live database server | Completed | 2017-08-30
tas.Pr_SetOvertimeWorkflowState | tas2 | Stored Procedure | This stored procedure is used to process the workflow of the "Overtime Online Approval System" | C:\NET Projects\GARMCO TAS V3\GARMCO.AMS.TAS\DBScripts\CreateScripts\StoredProcedures | Create | 1 | 2017-07-26 | New stored procedure | DB object already synchronized with the live database server | Completed | 2017-08-30
tas.Pr_GetCostCenterOTAllowed | tas2 | Stored Procedure | This stored procedure is used to fetch all cost centers where overtime is allowed | C:\NET Projects\GARMCO TAS V3\GARMCO.AMS.TAS\DBScripts\CreateScripts\StoredProcedures | Create | 1 | 2017-08-28 | New stored procedure | DB object already synchronized with the live database server | Completed | 2017-08-30
tas.Pr_GetOvertimeByPeriod | tas2 | Stored Procedure | Retrieve the employee overtime records | C:\NET Projects\GARMCO TAS V3\GARMCO.AMS.TAS\DBScripts\CreateScripts\StoredProcedures | Create | 1.2 | 2017-09-06 | Added extra logic in fetching the Approval Level description that fecth data using the "fnGetCurrentApprovalLevel" function | DB object already synchronized with the live database server | Completed | 2017-09-06
tas.Pr_GetAssignedOvertimeRequest | tas2 | Stored Procedure | Get the currently assigned overtime requisitions | C:\NET Projects\GARMCO TAS V3\GARMCO.AMS.TAS\DBScripts\CreateScripts\StoredProcedures | Update | 1.1 | 2017-09-06 | Added extra logic in fetching the Approval Level description that fecth data using the "fnGetCurrentApprovalLevel" function | DB object already synchronized with the live database server | Completed | 2017-09-06
tas.Pr_GetOvertimeRequisition | tas2 | Stored Procedure | Get the overtime requisitions | C:\NET Projects\GARMCO TAS V3\GARMCO.AMS.TAS\DBScripts\CreateScripts\StoredProcedures | Update | 1.1 | 2017-09-06 | Added extra logic in fetching the Approval Level description that fecth data using the "fnGetCurrentApprovalLevel" function | DB object already synchronized with the live database server | Completed | 2017-09-06
tas.Pr_ManageOvertimeRequest | tas2 | Stored Procedure | This stored procedure is used to manage a submitted overtime request | C:\NET Projects\GARMCO TAS V3\GARMCO.AMS.TAS\DBScripts\CreateScripts\StoredProcedures | Create | 1 | 2017-07-26 | New stored procedure | DB object already synchronized with the live database server | Completed | 2017-09-02
tas.fnGetCurrentApprovalLevel | tas2 | UDF | This UDF is used to get the approval level description of the current WF activity | C:\NET Projects\GARMCO TAS V3\GARMCO.AMS.TAS\DBScripts\CreateScripts\UserDefinedFunctions | Create | 1 | 2017-09-06 | New UDF | DB object already synchronized with the live database server | Completed | 2017-09-06
tas.fnCheckIfCreatorIsSupervisor | tas2 | UDF | This function is used to check if the creator of the overtime request is a Shift Supervisor | C:\NET Projects\GARMCO TAS V3\GARMCO.AMS.TAS\DBScripts\CreateScripts\UserDefinedFunctions | Create | 1 | 2017-09-12 | New UDF | DB object already synchronized with the live database server | Completed | 2017-09-13
tas.fnCheckIfArrivedEarly | tas2 | UDF | This function is used to check if an employee came to work earlier than the shaving time allowance | C:\NET Projects\GARMCO TAS V3\GARMCO.AMS.TAS\DBScripts\CreateScripts\UserDefinedFunctions | Create | 1 | 2017-09-12 | New UDF | DB object already synchronized with the live database server | Completed | 2017-09-13
tas.Vw_ShiftSupervisor | tas2 | View | Get the list of all Shift Supervisors | C:\NET Projects\GARMCO TAS V3\GARMCO.AMS.TAS\DBScripts\CreateScripts\Views | Create | 1 | 2017-09-12 | New view | DB object already synchronized with the live database server | Completed | 2017-09-13

## Setup
DB Object Type | Type of Change | System Name | Permission Type | Status | Source Code Layer | Implementation Status
Table | Create | TAS | Insert | Pending | Front-end (UI design) | Implemented in Production
View | Update | DIL Module | Update | Completed | Front-end (code behind) | Testing completed
UDF |  |  | Delete | Work In Progress | DAL | Pending for Testing
Stored Procedure |  |  | Select |  | Business Logic | Not used
Synonym |  |  | All
Data